## Dashboard
FYP IMPLEMENTATION TRACKER — Bookability Prediction System
Real-Time Bookability Prediction Using Calibrated Multi-Class ML ¦ Target: 80+ / 100
KEY METRICS
Current Mark |  | Target Mark |  | Marks Gap |  | Marks Recovered | Projected Mark
26 |  | 80
Total Tasks |  | Done |  | % Complete
PROGRESS (each filled cell ≈ 4 marks ¦ 🔵 Done ⬜ Remaining)
█ | █ | █ | █
🎯 PRIORITY ACTION BOARD — Highest-Impact Tasks (ordered by marks recovery)
# | Task ID | Description | File | Marks Recovered | Priority | Status
1 | P4-2 | Implement Temperature Scaling (calibrate.py) | calibrate.py (new) | +12 | CRITICAL | Not Started
2 | P3-1 | Create held-out temporal test set split | split.py (new) | +8 | CRITICAL | Not Started
3 | P8-1 | Multi-model comparison experiment (LR/RF/LightGBM/CatBoost) | model_comparison.py | +6 | CRITICAL | Not Started
4 | P4-5 | Compute ECE per class (pre + post calibration) | calibrate.py | +6 | CRITICAL | Not Started
5 | P8-2 | Calibration method comparison experiment | calibrate.py | +5 | CRITICAL | Not Started
6 | P5-1 | Rewrite evaluate_model.py to use test set only | evaluate_model.py | +5 | CRITICAL | Not Started
7 | P3-2 | Fix model selection: accuracy → log_loss | train_production.py:113 | +4 | CRITICAL | Not Started
8 | P1-1 | Fix search_day bug (.day → .weekday()) | app.py:105 | +2 | CRITICAL | Not Started
9 | P5-5 | SHAP feature importance analysis | evaluate_model.py | +4 | High | Not Started
10 | P4-6 | Generate reliability diagrams (pre/post calibration) | calibrate.py | +3 | CRITICAL | Not Started

## Phase Tracker
Task ID | Phase | Task Name | Description | File to Edit | LOC Est. | Marks at Stake | Priority | Status | Marks Recovered | Notes
PHASE 0 — Problem Formulation
P0-1 | Phase 0 | Write Formal Hypotheses | Add H1 (CatBoost outperforms baselines), H2 (calibration reduces ECE), H3 (sub-100ms achieved) | README.md | 20 | 2 | High | Not Started |  | Research paper requirement
P0-2 | Phase 0 | Define Success Criteria | Document ECE<0.05, macro-F1>0.70, p99<100ms targets | README.md | 15 | 1 | Medium | Not Started |  | Must appear in methodology section
P0-3 | Phase 0 | Class Semantic Documentation | Document Booked/PM/NA/NB operationally with business cost | README.md | 30 | 1 | Medium | Not Started |  | Required for data section of paper
P0-4 | Phase 0 | Create constants.py shared module | Move outcome_map, feature_order into one importable file — fixes TripAdvisor inconsistency | constants.py (new) | 25 | 1 | High | Not Started |  | Fixes class gap across 3 files
PHASE 1 — Data Pipeline
P1-1 | Phase 1 | Fix search_day bug in app.py | CRITICAL: Change line 105 from search_date.day to search_date.weekday() | app.py line 105 | 1 | 2 | CRITICAL | Not Started |  | 1-character fix — do first
P1-2 | Phase 1 | Add data quality logging | Log rows dropped per filter: NaT dates, negative days, dropna count, final class dist | process_full_data.py | 30 | 1 | High | Not Started |  | Required for paper's data section
P1-3 | Phase 1 | Add schema validation | Assert REQUIRED_COLS present before processing begins | process_full_data.py | 15 | 1 | High | Not Started |  | Prevents silent schema failures
P1-4 | Phase 1 | Fix meta engine dropdown in app.py | Add 'Direct' and 'TripAdvisor' to meta_engine_options — training classes not selectable | app.py line 44 | 3 | 1 | CRITICAL | Not Started |  | Fixes training-serving class gap
P1-5 | Phase 1 | Add advanced temporal features | Add hours_to_departure, dep_day_of_week, booking_window_bucket, is_red_eye | process_full_data.py | 20 | 2 | High | Not Started |  | 5 missing features from pipeline
P1-6 | Phase 1 | Fix exception handling | Replace bare except: with except Exception as e: logging.warning(...) | process_full_data.py | 5 | 0.5 | Medium | Not Started |  | Bare except swallows all errors
PHASE 2 — Feature Engineering
P2-1 | Phase 2 | Add route_cabin interaction feature | origin+dest+cabin inside CV fold loop to capture premium seat scarcity on routes | train_production.py | 4 | 1 | High | Not Started
P2-2 | Phase 2 | Add engine_window interaction feature | meta_engine+booking_window_bucket inside fold loop | train_production.py | 4 | 1 | High | Not Started
P2-3 | Phase 2 | Remove dead target_encode() function | Delete lines 42-58: defined but never called — misleads examiner | train_production.py | 0 | 1 | Medium | Not Started |  | Delete 17 lines of dead code
P2-4 | Phase 2 | Remove unused imports | Remove import joblib from train_production.py and app.py | Multiple files | 2 | 0.5 | Low | Not Started |  | Dead imports
P2-5 | Phase 2 | Add log(days+1) feature | log1p transform of days_to_departure as additional numerical feature | train_production.py + app.py | 4 | 1.5 | Medium | Not Started |  | Compresses right-skewed distribution
PHASE 3 — Model Training
P3-1 | Phase 3 | Create train/cal/test split script | CRITICAL: Save last 20% by booking_time as test set BEFORE any training. Save X_test.pkl, y_test.pkl | split.py (new) | 40 | 5 | CRITICAL | Not Started |  | Prerequisite for all valid evaluation
P3-2 | Phase 3 | Fix model selection criterion | Change model.score() (accuracy) to log_loss() for best fold selection in CV loop | train_production.py line 113 | 5 | 3 | CRITICAL | Not Started |  | Accuracy on imbalanced data = wrong metric
P3-3 | Phase 3 | Add multi-metric CV tracking | Track log_loss, macro_f1, pm_f1, brier_score per fold (not just accuracy) | train_production.py | 25 | 2 | High | Not Started
P3-4 | Phase 3 | Generate confusion matrix PNG | Add seaborn heatmap + plt.savefig() — was promised in config but never created | train_production.py | 15 | 1 | High | Not Started |  | CONFUSION_MATRIX_FILE declared but unused
P3-5 | Phase 3 | Save model metadata JSON | Save training date, feature list, CV scores, hyperparams to model_metadata.json | train_production.py | 20 | 1 | Medium | Not Started
P3-6 | Phase 3 | Multi-model comparison experiment | Train LR, RF, LightGBM, CatBoost on same CV folds — compare log-loss/macro-F1/PM-F1 | model_comparison.py (new) | 80 | 6 | CRITICAL | Not Started |  | Required to justify CatBoost choice
PHASE 4 — Probability Calibration ← CORE RESEARCH CONTRIBUTION
P4-1 | Phase 4 | Create calibration split | Hold out 20% of training data as calibration set (separate from test set) | split.py | 10 | 2 | CRITICAL | Not Started |  | Prerequisite for all calibration work
P4-2 | Phase 4 | Implement Temperature Scaling | Fit optimal T on cal set via scipy.optimize NLL minimisation — the key research method | calibrate.py (new) | 40 | 5 | CRITICAL | Not Started |  | Single parameter, zero overfitting risk
P4-3 | Phase 4 | Implement Platt Scaling | Per-class logistic regression on calibration set probabilities (OvR) | calibrate.py | 25 | 2 | High | Not Started |  | Comparison method
P4-4 | Phase 4 | Implement Isotonic Regression | Per-class IsotonicRegression calibration (OvR, non-parametric) | calibrate.py | 20 | 2 | High | Not Started |  | Comparison method
P4-5 | Phase 4 | Compute ECE per class | Implement compute_ece() for all 4 classes before and after each calibration method | calibrate.py | 30 | 3 | CRITICAL | Not Started |  | Primary calibration metric for paper
P4-6 | Phase 4 | Generate reliability diagrams | 4-panel reliability plot (pre + post calibration) using calibration_curve | calibrate.py | 30 | 3 | CRITICAL | Not Started |  | Primary research figure for paper
P4-7 | Phase 4 | Calibration comparison table | Table: Uncalibrated vs Platt vs Isotonic vs Temperature — ECE per class + log-loss | calibrate.py | 20 | 3 | CRITICAL | Not Started |  | Key results table for paper
P4-8 | Phase 4 | Save calibration artifact | Persist optimal T and method to calibration_params.pkl | calibrate.py | 5 | 1 | High | Not Started
P4-9 | Phase 4 | Apply calibration in app.py | Load calibration_params.pkl and apply temperature_scale() before displaying probs | app.py | 20 | 3 | CRITICAL | Not Started |  | Currently shows raw uncalibrated outputs
PHASE 5 — Model Evaluation
P5-1 | Phase 5 | Rewrite evaluate_model.py — use test set | CRITICAL: Load X_test.pkl (never seen by model). All current metrics are in-sample/invalid | evaluate_model.py | 20 | 5 | CRITICAL | Not Started |  | Single most important evaluation fix
P5-2 | Phase 5 | Add per-class AUC-ROC curves | One-vs-Rest ROC curves for all 4 classes, save PNG | evaluate_model.py | 25 | 3 | High | Not Started
P5-3 | Phase 5 | Add Precision-Recall curves | PR curves per class (more informative than ROC for imbalanced data), save PNG | evaluate_model.py | 20 | 2 | High | Not Started
P5-4 | Phase 5 | Add Brier Score | Multi-class Brier score — gold standard for probabilistic classifiers | evaluate_model.py | 10 | 1 | High | Not Started
P5-5 | Phase 5 | SHAP feature importance analysis | shap.TreeExplainer — summary plots per class + waterfall for single prediction | evaluate_model.py | 30 | 4 | High | Not Started |  | Required for interpretability
P5-6 | Phase 5 | Export results to files | Save classification_report, confusion_matrix, calibration_table to CSV/PNG | evaluate_model.py | 15 | 1 | Medium | Not Started |  | Paper needs persistent tables
PHASE 6 — Real-Time Application
P6-1 | Phase 6 | Add cabin class labels | M (Economy), W (Premium Eco), C (Business), F (First) in dropdown | app.py | 5 | 0.5 | Low | Not Started |  | UX improvement
P6-2 | Phase 6 | Add input validation | Block origin == destination; add date min_value constraints | app.py | 10 | 0.5 | Medium | Not Started
P6-3 | Phase 6 | Add baseline reference to chart | Horizontal line at 0.25 (random chance) and training prior on probability bar chart | app.py | 8 | 0.5 | Medium | Not Started
P6-4 | Phase 6 | Add SHAP local explanation in app | Waterfall SHAP plot explaining why the specific prediction was made | app.py | 20 | 2 | High | Not Started |  | Transforms demo from black-box to explainable
P6-5 | Phase 6 | Display model metadata in sidebar | Show model version, training date, CV scores from model_metadata.json | app.py | 15 | 1 | Medium | Not Started
P6-6 | Phase 6 | Add calibration note/disclaimer to UI | State that probabilities are temperature-scaled calibrated outputs | app.py | 3 | 0.5 | High | Not Started |  | Academic honesty — title says Calibrated
PHASE 7 — MLOps
P7-1 | Phase 7 | Replace print() with logging | import logging; replace all print() with logging.info() / logging.warning() | All .py files | 30 | 1 | Medium | Not Started
P7-2 | Phase 7 | Write model card | Document: version, training data stats, performance, known limitations | model_card.md (new) | 60 | 1 | Medium | Not Started
P7-3 | Phase 7 | Pin Python/package versions | Add python_requires and version pins to requirements.txt | requirements.txt | 10 | 0.5 | Low | Not Started
P7-4 | Phase 7 | Add training-serving skew test | Assert feature value ranges at inference match training distributions | app.py | 15 | 0.5 | Medium | Not Started
PHASE 8 — Experiments & Research Paper
P8-1 | Phase 8 | Exp E-D6.1: Algorithm comparison | Run and document LR vs RF vs LightGBM vs CatBoost — log-loss, macro-F1, PM-F1, AUC | experiments/algo_comparison.py (new) | 80 | 3 | CRITICAL | Not Started |  | Justifies CatBoost selection
P8-2 | Phase 8 | Exp E-D8.1: Calibration method comparison | Platt vs Isotonic vs Temperature vs Dirichlet — ECE + AUC tradeoff table | experiments/calibration_exp.py (new) | 60 | 3 | CRITICAL | Not Started |  | Core research experiment
P8-3 | Phase 8 | Exp E-D5.1: Imbalance strategy | auto_balanced vs SMOTE vs custom_weights(2.5x PM) comparison | experiments/imbalance_exp.py (new) | 50 | 1 | Medium | Not Started
P8-4 | Phase 8 | Exp E-D2.3: Feature ablation | With/without interaction features — measure delta log-loss per interaction added | experiments/feature_ablation.py (new) | 40 | 2 | High | Not Started
P8-5 | Phase 8 | Exp E-D4.2: CV fold count | Compare K=3,5,10 — stability of log-loss std across folds | experiments/cv_folds_exp.py (new) | 30 | 1 | Low | Not Started

## Mark Recovery Plan
MARK RECOVERY PLAN — From 26/100 → 80+/100
Milestone | Tasks Included | Marks Recovered | Cumulative Mark | Grade Band | Effort (Hours) | Status
STARTING POINT | Current submitted code | 0 | 26 | FAIL (below 40) | — | Current
Milestone 1: Fix Critical Bugs | P1-1, P1-4, P0-4, P3-2 | 7 | 33 | FAIL (approaching pass) | 1 hour | Not Started
Milestone 2: Valid Evaluation Foundation | P3-1, P5-1, P1-2, P1-3 | 11 | 44 | THIRD CLASS (Pass) | 4 hours | Not Started
Milestone 3: Core Research Contribution | P4-1, P4-2, P4-5, P4-6, P4-9 | 16 | 60 | LOWER SECOND (2:2) | 8 hours | Not Started
Milestone 4: Comparative Evidence | P3-6, P8-1, P8-2, P4-3, P4-4 | 10 | 70 | UPPER SECOND (2:1) | 10 hours | Not Started
Milestone 5: Evaluation Depth | P5-2, P5-3, P5-4, P5-5, P4-7 | 9 | 79 | UPPER SECOND (2:1) | 8 hours | Not Started
Milestone 6: First Class Territory | P8-3, P8-4, P3-3, P2-1, P2-2, P0-1, P7-2 | 8 | 87 | FIRST CLASS ★ | 10 hours | Not Started
Full Completion | All remaining tasks | 5 | 92 | FIRST CLASS (High) ★★ | 6 hours | Not Started
CRITICAL PATH — Minimum 16 Tasks Required to Reach 80 Marks
Task ID | Description | Marks at Stake | Phase | Why It Matters
P1-1 | Fix search_day bug (.day → .weekday()) | 2 | Phase 1 | Every prediction is wrong for search_day feature — 1 line fix
P1-4 | Fix meta engine options (add Direct, TripAdvisor) | 1 | Phase 1 | Training classes not selectable at inference — creates prediction gap
P0-4 | Create constants.py shared module | 1 | Phase 0 | Fixes TripAdvisor inconsistency across 3 files
P3-1 | Create held-out temporal test set | 5 | Phase 3 | Without this, ALL evaluation metrics are invalid — prerequisite for paper
P3-2 | Fix model selection criterion (log_loss not accuracy) | 3 | Phase 3 | Currently saves wrong 'best' model — accuracy is misleading on imbalanced data
P3-6 | Multi-model comparison (LR/RF/LightGBM/CatBoost) | 6 | Phase 3 | Cannot claim CatBoost is best without comparison — required by examiner
P4-1 | Create calibration split | 2 | Phase 4 | Prerequisite for all calibration work
P4-2 | Implement Temperature Scaling | 5 | Phase 4 | THE core research contribution — title says Calibrated — must exist
P4-5 | Compute ECE per class | 3 | Phase 4 | Primary calibration metric — must appear in results tables
P4-6 | Generate reliability diagrams | 3 | Phase 4 | Primary calibration figure for paper
P4-7 | Calibration method comparison table | 3 | Phase 4 | Justifies choice of Temperature Scaling over Platt/Isotonic
P4-9 | Apply calibration in app.py | 3 | Phase 6 | App currently shows uncalibrated probs — contradicts research title
P5-1 | Rewrite evaluate_model.py — use test set | 5 | Phase 5 | All current metrics are in-sample — invalid for a research paper
P5-5 | SHAP feature importance analysis | 4 | Phase 5 | Required for interpretability claim — examiner expects this
P8-1 | Algorithm comparison experiment | 3 | Phase 8 | Documents why CatBoost was chosen — justification for design decision
P8-2 | Calibration method comparison experiment | 3 | Phase 8 | Documents why Temperature Scaling was chosen — core research experiment

## Sprint Planner
SPRINT PLANNER — 6-Week Execution Plan to 80+ Marks
Week | Sprint Goal | Task IDs | Key Deliverables | Marks Gained | Cumulative Mark | Effort (Hours) | Status
Week 1 | Foundation Fixes & Code Cleanup | P1-1, P1-4, P0-4, P3-2, P1-2, P1-3, P2-3, P2-4 | • Fix search_day bug (1 line) • Fix meta engine options • Create constants.py • Fix model selection to log_loss • Remove dead code | +8 | 34 | ~6 hrs | Not Started
Week 2 | Valid Evaluation Foundation | P3-1, P3-6, P5-1, P8-1 | • split.py: temporal train/cal/test split • model_comparison.py: LR/RF/LightGBM/CatBoost table • Rewrite evaluate_model.py to use test set | +14 | 48 | ~12 hrs | Not Started
Week 3 | Full Calibration Pipeline | P4-1, P4-2, P4-3, P4-4, P4-5, P4-6, P4-7, P4-8, P4-9 | • calibrate.py: Temperature + Platt + Isotonic • Reliability diagrams (pre/post) saved as PNG • ECE per class computed • Calibration comparison table • App shows calibrated probabilities | +22 | 70 | ~16 hrs | Not Started
Week 4 | Deep Evaluation & Experiments | P5-2, P5-3, P5-4, P5-5, P5-6, P8-2, P3-4, P3-5 | • AUC-ROC & PR curves per class • SHAP summary plots per class • Brier score computed • Results exported to CSV • Calibration method comparison experiment | +12 | 82 | ~14 hrs | Not Started
Week 5 | Feature Experiments & App Enhancement | P8-3, P8-4, P2-1, P2-2, P0-1, P6-4, P6-5 | • Imbalance strategy experiment • Feature ablation experiment • route_cabin + engine_window features added • SHAP waterfall in Streamlit app • Formal hypotheses written | +8 | 90 | ~10 hrs | Not Started
Week 6 | Documentation & Polish | P7-1, P7-2, P7-3, P0-2, P0-3, P6-1, P6-2, P6-6, P8-5 | • logging module replacing all print() • Model card written • Success criteria documented • App UI polished with labels & validation • Calibration disclaimer added | +4 | 94 | ~6 hrs | Not Started
MARK TRAJECTORY
Start | W1 End | W2 End | W3 End | W4 End | W5 End | W6 End
26 | 34 | 48 | 70 | 82 | 90 | 94

## Bugs Registry
BUGS REGISTRY — All Known Issues & Required Fixes
Bug ID | Severity | File | Line(s) | Bug Description | Impact on Results | Fix Required | Fix Complexity | Status | Marks Risk
BUG-001 | CRITICAL | app.py | 105 | search_date.day returns calendar day 1–31. Model trained on dayofweek 0–6. | EVERY prediction uses wrong search_day value — training-serving skew on every single inference call | Change .day to .weekday() | 1 line | Not Fixed | 2
BUG-002 | CRITICAL | evaluate_model.py | 10, 54 | Model evaluated on the full training dataset including rows it was trained on | ALL reported metrics are in-sample. Inflated by 10–20 percentage points. Not publishable. | Create and load held-out test set (X_test.pkl) | 40 lines | Not Fixed | 10
BUG-003 | CRITICAL | All files | N/A | Zero calibration code exists anywhere despite 'Calibrated' in research title | Displayed probabilities are raw overconfident GBDT outputs — research title claim is unsubstantiated | Implement Temperature Scaling in calibrate.py + apply in app.py | 60 lines | Not Fixed | 22
BUG-004 | CRITICAL | train_production.py | 113 | model.score() (accuracy) used to select the 'best model' fold | Best model is the one on the easiest fold by accuracy, not the best probabilistic predictor. PM class ignored. | Change to log_loss-based selection | 5 lines | Not Fixed | 3
BUG-005 | MAJOR | app.py | 44 | TripAdvisor and Direct missing from meta_engine_options dropdown | Users cannot represent these channels. Model receives out-of-distribution input silently. | Add 'TripAdvisor' and 'Direct' to list | 2 lines | Not Fixed | 1
BUG-006 | MAJOR | train_production.py | 12 | CONFUSION_MATRIX_FILE variable declared but confusion_matrix.png never generated | Promised evaluation artifact missing. Examiner expects this figure. | Add seaborn heatmap + plt.savefig() call | 15 lines | Not Fixed | 1
BUG-007 | MAJOR | train_production.py | 42–58 | target_encode() function defined but never called — 17 lines of dead code | Misleads examiner into thinking target encoding is performed. Undermines credibility. | Delete function entirely or add a call to it | Delete 17 lines | Not Fixed | 1
BUG-008 | MAJOR | Multiple files | Multiple | outcome_map and feature_order duplicated identically across 3 files | Any label change requires updating 3 files. One will be missed. Source of TripAdvisor gap. | Create constants.py and import from all scripts | 25 lines | Not Fixed | 1
BUG-009 | MODERATE | Multiple files | Multiple | import joblib, log_loss, plt, sns, confusion_matrix imported but never used | Dead imports. Reduces code quality. log_loss import suggests metrics were intended but skipped. | Remove all unused imports | 3 lines | Not Fixed | 0
BUG-010 | MODERATE | process_full_data.py | 87 | Typo: "Propcessing" instead of "Processing" in print statement | Professional presentation issue — visible in demo output | Fix typo | 1 line | Not Fixed | 0
TOTAL MARKS AT RISK FROM UNFIXED BUGS