## Master_Tracking_Sheet
Flight Bookability Research Project - Master Formative Tracking Sheet
This single sheet consolidates all 9 master improvement areas, issues, required fixes, and code references discussed in the review.
ID | Master Improvement Area | Stage | Issue | Problem Description | Improvement / Fix Required | Code Fix Reference | Priority | Implementation Notes | Dependency / Data Needed | Status
1 | Problem Formulation & Label Engineering | Target Design | Incorrect class definition | 'Not Booked' used as a valid clean class although it may reflect abandonment rather than unbookability | Introduce proper class taxonomy: bookable, price_changed, unavailable, technical_failure, ambiguous | DEFAULT_LABEL_MAP / TARGET_CLASSES | High | Needs redesign of target labels | None | Pending
2 | Problem Formulation & Label Engineering | Target Design | Missing technical failure class | Supplier / redirect / timeout failures are not modeled | Add technical_failure class and map technical statuses explicitly | TARGET_CLASSES | High | Add class to label pipeline | Status values or failure logs | Pending
3 | Problem Formulation & Label Engineering | Target Design | No ambiguous handling | Noisy or weak labels treated as ground truth | Add ambiguous class with lower confidence | build_labels() | High | Separate ambiguous outcomes from strong labels | Status values | Pending
4 | Problem Formulation & Label Engineering | Label Engineering | Direct mapping only | No robust label derivation / normalization logic | Normalize raw status strings before mapping | canonicalize_label() | High | Centralize label normalization | Raw status field | Pending
5 | Problem Formulation & Label Engineering | Label Engineering | No label confidence | All labels weighted equally despite differing reliability | Add label_confidence column and use for auditing / future weighting | build_labels() | Medium | Add confidence metadata | Label mapping logic | Pending
6 | Data Preprocessing & Cleaning | Schema Validation | Columns used before checking existence | Can cause runtime crashes and fragile preprocessing | Validate schema before any column access | validate_schema() | High | Detect required and optional columns first | None | Pending
7 | Data Preprocessing & Cleaning | Timestamp Handling | Wrong inference-time assumption | Using LandingTime as booking_time can create leakage and wrong operational framing | Introduce explicit prediction_time chosen from true inference-time column | preprocess_dataframe() | High | Rename and standardize inference timestamp | Correct timestamp source | Pending
8 | Data Preprocessing & Cleaning | Data Cleaning | No preprocessing audit | No visibility into rows dropped or parsing failures | Create audit dictionary for all cleaning steps | audit = {} | Medium | Track row counts by cleaning reason | None | Pending
9 | Data Preprocessing & Cleaning | Data Quality | No duplicate removal | Duplicate offers can bias class frequencies and model learning | Add deduplication rules using provider/route/airline/price/time | drop_duplicates() | High | Deduplicate near-identical offers | Core columns present | Pending
10 | Data Preprocessing & Cleaning | Missing Data | Blind dropna() | Rows are removed without understanding impact or preserving useful missingness | Use controlled filtering with explicit required columns only | required_postmap | High | Replace blanket dropna | None | Pending
11 | Data Preprocessing & Cleaning | Date Logic | Negative days_to_departure removed blindly | No reporting or diagnosis of time anomalies | Track and log removals before filtering negatives | audit["rows_negative_days_to_departure"] | Medium | Audit date inconsistencies | Parsed timestamps | Pending
12 | Feature Engineering | Feature Depth | Very weak feature set | Current model lacks most operationally useful predictors | Build richer engineered feature layer | engineer_features() | High | Expand from basic route/time features | Data availability dependent | Pending
13 | Feature Engineering | Price Features | No relative price modeling | Model cannot compare an offer against market context | Add price_gap_to_min, price_ratio_to_median, route_day_min_price, route_day_median_price | price_gap_to_min / price_ratio_to_median | High | Create relative price signals | Price column needed | Pending
14 | Feature Engineering | Provider Signals | No provider reliability features | Model cannot identify historically unreliable suppliers | Add provider prior rates by class | add_group_rolling_rates() | High | Engineer provider historical reliability | Provider identifier needed | Pending
15 | Feature Engineering | Temporal Features | No recency / freshness signals | No proxy for recent instability or activity | Add minutes_since_prev features per provider/route/provider_route | minutes_since_prev | High | Create recency features | Timestamp + grouping keys | Pending
16 | Feature Engineering | Competition Features | No market context features | Model misses competition density and route activity | Add route_search_density and provider_offer_density | route_search_density / provider_offer_density | Medium | Add competition proxies | Grouping keys | Pending
17 | Feature Engineering | Missing Indicators | No missingness flags | Model is blind to informative missing values | Add missing_price and unknown_provider indicators | missing_price / unknown_provider | Low | Create binary missingness flags | Relevant fields | Pending
18 | Temporal Design & Leakage | Temporal Split | Only one holdout split used | Weak validation and limited evidence of time robustness | Use train/validation/test chronological split | temporal_split() | High | Establish contiguous temporal partitions | prediction_time | Pending
19 | Temporal Design & Leakage | Leakage Risk | Future data used in aggregates | Historical rates may leak future outcomes if built naively | Use prior-only expanding counts and rates | cumcount() logic in add_group_rolling_rates() | High | Enforce point-in-time safe features | prediction_time order | Pending
20 | Temporal Design & Leakage | Validation Robustness | No rolling evaluation | No evidence model is stable across time windows | Add rolling backtests | rolling_backtest_splits() | High | Evaluate across multiple out-of-time windows | Sufficient row count | Pending
21 | Model Development | Model Variety | Only CatBoost used | No baseline comparison to justify final model choice | Train logistic regression and random forest alternatives alongside CatBoost | train_model_alternatives() | High | Implement comparative model set | Feature matrix | Pending
22 | Model Development | Model Selection | No model selection logic | Final model is chosen arbitrarily | Select best model using validation macro F1 and log loss | select_best_model() | High | Adopt evidence-based model selection | Validation results | Pending
23 | Model Development | Hyperparameters | No structured tuning | Suboptimal performance likely | Use stronger CatBoost settings and later extend to tuning | CatBoost config | Medium | Refine hyperparameters | Validation set | Pending
24 | Model Development | Imbalance Handling | Weak class imbalance handling | Rare failure modes may be underlearned | Use auto class weights / balanced learning | auto_class_weights | Medium | Strengthen class handling | Class distribution | Pending
25 | Calibration | Calibration Depth | Only isotonic used | Single-method calibration is weak evidence | Compare multiple calibration methods | calibration classes | High | Evaluate alternative calibrators | Validation probabilities | Pending
26 | Calibration | Calibration Type | No temperature scaling | May miss simpler stable calibration improvement | Add TemperatureScaler | TemperatureScaler | High | Implement temperature scaling | Validation probabilities | Pending
27 | Calibration | Multiclass Calibration | Incorrect / weak multiclass approach | Independent isotonic fits may distort class probability simplex | Add MultinomialLogitCalibrator | MultinomialLogitCalibrator | High | Use stronger multiclass calibrator | Validation probabilities | Pending
28 | Calibration | Selection | No calibration comparison | Best calibration method is not justified | Select best calibrator using validation log loss and macro F1 | select_best_calibrator() | High | Choose calibration empirically | Validation results | Pending
29 | Evaluation Metrics | Metrics Coverage | Missing macro/weighted F1 | Evaluation is incomplete for multi-class imbalance | Add macro F1 and weighted F1 | evaluate_predictions() | High | Expand classification metrics | Predictions | Pending
30 | Evaluation Metrics | Classification Insight | No confusion matrix | No visibility into class-level errors | Add confusion matrix to evaluation output | evaluate_predictions() | High | Improve error diagnostics | Predictions | Pending
31 | Evaluation Metrics | Calibration Metrics | Limited calibration evaluation | Probability quality not fully assessed | Add multiclass Brier and classwise ECE | evaluate_predictions() | High | Improve calibration diagnostics | Predictions | Pending
32 | Evaluation Metrics | Class-Level Analysis | No per-class evaluation | Hard to assess rare failure classes | Add class-wise metric breakdowns | ECE loop / classification_report | Medium | Report class-level quality | Predictions | Pending
33 | Business Logic & Policy Simulation | Simulation Quality | Unrealistic bid simulation | Original business evaluation is not aligned to metasearch ranking/suppression use case | Replace with suppression and reranking simulation | policy_simulation() | High | Align evaluation to real metasearch usage | Predicted probabilities | Pending
34 | Business Logic & Policy Simulation | Suppression Logic | No risk thresholds | Cannot operationalize high-risk offer filtering | Compute risk_unbookable and threshold-based suppression | risk_unbookable | High | Implement suppression policy | Predicted probabilities | Pending
35 | Business Logic & Policy Simulation | Ranking Logic | No reranking evaluation | No estimate of ML value in top displayed results | Create rank_score_ml using bookable probability and risk | rank_score_ml | High | Implement reranking proxy | Predicted probabilities + price if available | Pending
36 | Business Logic & Policy Simulation | Business Metrics | No operational KPI evaluation | Weak real-world usefulness evidence | Add top-1 bookable rate before vs after ML | policy_simulation() | High | Measure display-quality improvement | Grouped test data | Pending
37 | Engineering & Pipeline | Pipeline Structure | Notebook-only implementation | Difficult to reuse, validate, and productionize | Create full main pipeline | main_pipeline() | High | Move from notebook to structured pipeline | All prior modules | Pending
38 | Engineering & Pipeline | Reproducibility | No saved outputs or audit artifacts | Hard to trace runs and compare experiments | Persist config, mapping, audit, split metadata, results JSON | save_json() | Medium | Add reproducibility artifacts | Output directory | Pending
39 | Engineering & Pipeline | Feature Tracking | No saved feature lists | Hard to debug feature usage and comparisons | Save categorical and numeric feature lists | feature_lists.json | Low | Track exact feature sets | Feature builder | Pending
40 | Engineering & Pipeline | Model Persistence | No model persistence workflow | Model cannot be reused or deployed cleanly | Save best model and calibrators to disk | joblib / CatBoost save | High | Persist final artifacts | Trained model objects | Pending
Legend
High | Critical fix needed
Medium | Important improvement
Low | Useful enhancement